HỆ THỐNG QUẢN LÝ GIAO HÀNG ELog

KẾ HOẠCH PHÁT TRIỂN TĂNG DẦN & JIRA BACKLOG

Incremental Development Plan — Web Dashboard & Driver Mobile App

Dự án: ELog Delivery Management System (SEP490_G104)

Lĩnh vực: Electronics Logistics / Warehouse-to-Store Delivery

Mô hình: Phát triển tăng dần | Đội ngũ: 5 thành viên | Sprint: 2 tuần

Stack đề xuất: Java Spring Boot · MySQL · ReactJS · Mobile App · REST API · JWT

Nguồn sự thật đã cập nhật: Report 1 — Vision & Scope v1.0.8, Last Updated 07/06/2026

# 1. Phân tích & Cơ sở sửa kế hoạch

Tài liệu này là bản kế hoạch phát triển tăng dần đã được chỉnh sửa để khớp với Report 1 mới nhất. Các điểm sửa chính tập trung vào phạm vi hệ thống, stakeholder, feature boundary, thứ tự triển khai và backlog cho Driver Mobile App.

| Hạng mục | Bản kế hoạch cũ | Sửa theo Report 1 |
| --- | --- | --- |
| Phạm vi giao diện | Chỉ Web Dashboard; Driver App bị hoãn. | Bao gồm Web Dashboard cho Dispatcher/Warehouse Staff/Manager/Admin và Mobile App cho Driver. |
| Feature FE-06 | Đánh dấu Deferred vì phụ thuộc App tài xế. | Đưa vào phạm vi triển khai Iteration 3: Driver executes trips, updates milestones, captures e-POD. |
| Capacity validation | Tập trung m³ và có nhắc weight. | Chuẩn hóa thành dual-constraint: volume m³ + weight kg. Cả hai điều kiện phải pass trước dispatch. |
| ETA | ETA tuyến tính chung. | ETA tuyến tính dùng Haversine distance từ store GPS coordinates và average vehicle speed cấu hình trong hệ thống. |
| Actor | Dispatcher, Warehouse Staff, Driver, System Admin. | Bổ sung Logistics Manager/Business Owner cho KPI monitoring theo stakeholder analysis. |
| External systems | GPS/Google Maps được nhắc chung. | Tách rõ GPS Tracking Platform và Map Service Provider; Map chỉ dùng lấy tọa độ/setup, ETA tính offline. |

## 1.1 Phạm vi đã chốt theo Report 1

• ELog là hệ thống lightweight end-to-end cho SME electronics distributors, vận hành từ một kho trung tâm đến mạng lưới cửa hàng cố định.

• Order input chỉ qua Excel file upload; không có UI tạo/sửa/xóa đơn hàng thủ công.

• Hệ thống hỗ trợ fixed-route/bus-route logic, dynamic stop skipping, linear ETA, capacity validation theo m³ và kg, LIFO flat loading manifest, dispatch, trip monitoring và e-POD.

• Web Dashboard phục vụ Dispatcher, Warehouse Staff, Logistics Manager/Business Owner và System Administrator.

• Driver Mobile App nằm trong phạm vi để tài xế xem chuyến, cập nhật milestone, báo exception và submit e-POD.

## 1.2 Truy vết tính năng Report 1 → Increment

| FE | Feature theo Report 1 | Increment phụ trách | Gap | Priority/Iteration |
| --- | --- | --- | --- | --- |
| FE-01 | Import Orders via Excel & Auto-Assign to Fixed Routes | INC-2 | GAP-01, GAP-03 | High / Iteration 1 |
| FE-02 | Validate Dual-Constraint Vehicle Capacity & Determine LIFO Sequence | INC-3 | GAP-01, GAP-02 | High / Iteration 1 |
| FE-03 | Review Trip Draft, Manage Active Stops & Calculate Linear ETA | INC-3 | GAP-01, GAP-02 | High / Iteration 1 |
| FE-04 | Allocate Vehicles & Dispatch Delivery Trips | INC-4 | GAP-01, GAP-03 | High / Iteration 2 |
| FE-05 | Monitor Trip Progress & Record Operational Exceptions | INC-5 | GAP-01 | Medium / Iteration 2 |
| FE-06 | Execute Delivery Trips & Confirm e-POD (Mobile App) | INC-6 | GAP-01, GAP-02 | Medium / Iteration 3 |

## 1.3 Assumptions & Constraints

• Single centralized warehouse only; multi-warehouse and inter-depot routing are out of scope.

• No full ERP, accounting, heavy WMS, unrestricted TSP optimization, complex 3D packing simulation, or manual order creation module.

• Each store belongs to exactly one fixed route for automatic route assignment.

• LIFO is implemented as flat sequence sorting; no x/y/z cabin coordinate simulation.

• Map Service Provider is used to source store coordinates during master data setup; daily ETA calculation uses stored coordinates and Haversine formula.

• GPS location for monitoring is received from the Driver Mobile App through GPS Tracking Platform.

## 1.4 Đội ngũ & Vai trò

| Mã | Thành viên | Vai trò chính sau khi sửa |
| --- | --- | --- |
| BE1 | Phạm Tiến Phát | Backend Lead / Database / Auth / Master Data |
| BE2 | Nguyễn Xuân Nguyên Giáp | Backend Business Logic: Excel import, m³/kg capacity, LIFO, ETA, trip state |
| FE1 | Lê Thành Linh | Frontend Lead: Web dashboard architecture, planning & monitoring UI |
| FE2 | Đặng Đức Cương | Frontend + Mobile App Driver screens |
| QA | Nguyễn Đức Minh | QA / Test case / UAT support / Documentation |

# 2. Tổng quan Increment đã sửa

| Increment | Tên | Mục tiêu |
| --- | --- | --- |
| INC-1 | Foundation, Security & Master Data | Dựng nền tảng kỹ thuật, JWT/RBAC, quản lý user/role, route, store GPS, vehicle capacity m³/kg, product master. |
| INC-2 | Excel Order Import & Auto Route Assignment | Upload Excel, validate từng dòng, tự động map store-to-route, tạo Trip Draft và tính tổng volume/weight. |
| INC-3 | Trip Draft Review, Active Stops, ETA, Capacity & LIFO | Review Trip Draft, skip stops without orders, calculate linear ETA, validate m³/kg, generate LIFO manifest. |
| INC-4 | Vehicle Allocation & Dispatch | Chọn xe/tài xế phù hợp, lock trip, tạo loading/handover slip, gửi lệnh đến Driver Mobile App. |
| INC-5 | Trip Monitoring, Exceptions & KPI | Dashboard giám sát GPS/milestone/e-POD, cảnh báo delay/exception, báo cáo KPI vận hành. |
| INC-6 | Driver Mobile App & e-POD | Driver xem trip, LIFO unloading, cập nhật milestone, báo exception, chụp ảnh và lấy chữ ký e-POD. |

# 3. Backlog chi tiết: Epic → User Story → Technical Task

## INC-1 — Foundation, Security & Master Data

### EP-01 — Project Skeleton & Infrastructure

US-01 — User Story

As a Developer, I want Backend, Frontend, Mobile and Database skeletons so the team can implement on one consistent foundation.

| # | Task | Loại | Giờ | Mô tả | Phụ trách |
| --- | --- | --- | --- | --- | --- |
| 1 | Create initial MySQL schema and Flyway migration | Database | 6 | Create elog database, base migration, connection pool | BE1 |
| 2 | Initialize Spring Boot layered project | Backend | 8 | Controller/service/repository/domain structure; dependencies for Web/JPA/Security | BE1 |
| 3 | Initialize ReactJS dashboard shell | Frontend | 8 | Routing, layout shell, axios client, environment config | FE1 |
| 4 | Initialize Mobile App skeleton for Driver | Mobile | 8 | Login shell, navigation structure, API client placeholder | FE2 |
| 5 | Configure Git workflow and CI build | DevOps | 8 | Branch strategy, PR template, GitHub Actions build/test | BE2/QA |
| 6 | Write local setup README | Documentation | 4 | How to run BE/FE/Mobile/DB locally | QA |

Tổng ước lượng US-01: 42 giờ (≈ 7.0 ngày công)

## INC-1 — Foundation, Security & Master Data

### EP-02 — Authentication & RBAC

US-02 — User Story

As a system user, I want to log in securely and receive role-based access so I can use only authorized functions.

| # | Task | Loại | Giờ | Mô tả | Phụ trách |
| --- | --- | --- | --- | --- | --- |
| 1 | Design users, roles and user_roles tables | Database | 6 | Unique username/email; role mapping | BE1 |
| 2 | Implement Spring Security + JWT | Backend | 12 | Login API, access/refresh token, authentication filter | BE1 |
| 3 | Implement RBAC endpoint authorization | Backend | 8 | Role-to-permission mapping; 403 for unauthorized access | BE2 |
| 4 | Build web login and route guard | Frontend | 10 | Login form, token storage, role-based redirect | FE1 |
| 5 | Build mobile login flow | Mobile | 8 | Driver login, token storage, session expiry handling | FE2 |
| 6 | Test auth and authorization cases | Testing | 8 | Invalid login, expired token, unauthorized endpoint | QA |

Tổng ước lượng US-02: 52 giờ (≈ 8.7 ngày công)

## INC-1 — Foundation, Security & Master Data

### EP-03 — Master Data Management

US-03 — User Story

As a System Administrator, I want to manage users, routes, stores, vehicles and product master data so planning data is centralized and validated.

| # | Task | Loại | Giờ | Mô tả | Phụ trách |
| --- | --- | --- | --- | --- | --- |
| 1 | User/role management API and admin screen | Backend/Frontend | 20 | CRUD user, lock/unlock, assign roles | BE1/FE2 |
| 2 | Route and route_stop CRUD | Backend/Frontend | 24 | Route sequence, store-to-route mapping, sequence validation | BE2/FE2 |
| 3 | Store master with GPS coordinates | Backend/Frontend | 20 | Store code, address, lat/lng, route mapping; source coordinates from map provider | BE1/FE2 |
| 4 | Vehicle master with capacity m³/kg | Backend/Frontend | 18 | Vehicle plate, volume capacity, weight limit, availability status | BE2/FE1 |
| 5 | Product master with volume and weight | Backend/Frontend | 18 | SKU, dimensions, calculated volume_m3, weight_kg | BE1/FE2 |
| 6 | Master data validation and tests | Testing | 14 | Unique codes, capacity > 0, inactive dependency checks | QA |

Tổng ước lượng US-03: 114 giờ (≈ 19.0 ngày công)

## INC-2 — Excel Order Import & Auto Route Assignment

### EP-04 — Excel Import & Validation

US-04 — User Story

As a Dispatcher, I want to upload a structured Excel file so the system can validate daily orders without manual data entry.

| # | Task | Loại | Giờ | Mô tả | Phụ trách |
| --- | --- | --- | --- | --- | --- |
| 1 | Design order, order_item, import_batch and validation_error tables | Database | 8 | Store import file metadata, row-level errors and batch status | BE1 |
| 2 | Implement Excel parser | Backend | 12 | Read .xlsx, map columns to orders/items, handle multi-line orders | BE2 |
| 3 | Implement row-level validation rules | Backend | 12 | Required fields, date, qty > 0, store exists, SKU exists | BE2 |
| 4 | Build upload and validation preview UI | Frontend | 12 | Drag-and-drop file, progress, preview, row errors | FE1 |
| 5 | Test Excel templates and error cases | Testing | 10 | Missing columns, invalid type, duplicate order, unknown store/SKU | QA |

Tổng ước lượng US-04: 54 giờ (≈ 9.0 ngày công)

## INC-2 — Excel Order Import & Auto Route Assignment

### EP-05 — Auto-Assign Orders to Fixed Routes

US-05 — User Story

As a Dispatcher, I want imported orders to be automatically assigned to fixed routes so the system can create accurate Trip Drafts.

| # | Task | Loại | Giờ | Mô tả | Phụ trách |
| --- | --- | --- | --- | --- | --- |
| 1 | Implement store-to-route assignment service | Backend | 10 | Each store maps to exactly one active route | BE2 |
| 2 | Create Trip Draft generation service | Backend | 12 | Group orders sharing the same route into consolidated trip draft | BE2 |
| 3 | Calculate total volume and total weight per Trip Draft | Backend | 8 | Aggregate order_item qty * product volume/weight | BE1 |
| 4 | Build Trip Draft list screen | Frontend | 10 | Show route, active order count, total m³/kg, validation status | FE2 |
| 5 | Test route assignment and aggregation | Testing | 8 | Multiple orders per route, rounding, missing mapping | QA |

Tổng ước lượng US-05: 48 giờ (≈ 8.0 ngày công)

## INC-3 — Trip Draft Review, Active Stops, ETA, Capacity & LIFO

### EP-06 — Trip Draft Review, Active Stops & Linear ETA

US-06 — User Story

As a Dispatcher, I want to review Trip Drafts, active stops, skipped stops and linear ETA before capacity validation.

| # | Task | Loại | Giờ | Mô tả | Phụ trách |
| --- | --- | --- | --- | --- | --- |
| 1 | Implement active/skip stop service | Backend | 8 | Keep route sequence; skip stores without orders | BE2 |
| 2 | Implement Haversine ETA service | Backend | 12 | Use stored store coordinates and configurable average speed | BE2 |
| 3 | API for Trip Draft detail and ETA plan | Backend | 6 | Return stops, skipped stops, ETA and route summary | BE1 |
| 4 | Build Trip Draft review screen | Frontend | 12 | Active/skipped stops, ETA table, departure time adjustment | FE1 |
| 5 | Test ETA and stop skipping | Testing | 8 | ETA recalculates when departure time or skipped stops change | QA |

Tổng ước lượng US-06: 46 giờ (≈ 7.7 ngày công)

## INC-3 — Trip Draft Review, Active Stops, ETA, Capacity & LIFO

### EP-07 — Dual-Constraint Capacity & LIFO Manifest

US-07 — User Story

As a Dispatcher/Warehouse Staff, I want the system to validate vehicle capacity and generate LIFO manifest so the trip is physically feasible.

| # | Task | Loại | Giờ | Mô tả | Phụ trách |
| --- | --- | --- | --- | --- | --- |
| 1 | Implement volume and weight validation service | Backend | 10 | Compare total m³/kg against selected vehicle capacity | BE2 |
| 2 | Design loading_manifest and manifest_item tables | Database | 6 | Store flat loading/unloading sequence per trip draft | BE1 |
| 3 | Generate flat LIFO loading sequence | Backend | 12 | Last delivery stop loaded first; first stop loaded last | BE2 |
| 4 | Build capacity and LIFO review screens | Frontend | 12 | Capacity bars, pass/fail reasons, printable manifest | FE2 |
| 5 | Test boundary and LIFO cases | Testing | 10 | Equal capacity, over capacity, sequence validation | QA |

Tổng ước lượng US-07: 50 giờ (≈ 8.3 ngày công)

## INC-4 — Vehicle Allocation & Dispatch

### EP-08 — Vehicle Allocation, Trip Lock & Dispatch

US-08 — User Story

As a Dispatcher, I want to select a suitable vehicle and driver, lock the trip and dispatch instructions to the Driver Mobile App.

| # | Task | Loại | Giờ | Mô tả | Phụ trách |
| --- | --- | --- | --- | --- | --- |
| 1 | Design trip and trip_status_history tables | Database | 8 | Trip state machine, assignment, audit history | BE1 |
| 2 | Implement vehicle suggestion and assignment service | Backend | 10 | Filter available vehicles passing m³/kg requirements | BE2 |
| 3 | Implement trip locking and dispatch API | Backend | 10 | Prevent edits after dispatch; send instruction payload to mobile | BE1 |
| 4 | Generate loading/handover slip | Backend/Frontend | 10 | Printable/PDF slip with route, vehicle, items, LIFO manifest | BE2/FE1 |
| 5 | Build dispatch UI | Frontend | 12 | Vehicle/driver selection, readiness checklist, dispatch confirmation | FE1 |
| 6 | Test trip state transitions | Testing | 8 | Draft → validated → dispatched; duplicate dispatch prevention | QA |

Tổng ước lượng US-08: 58 giờ (≈ 9.7 ngày công)

## INC-5 — Trip Monitoring, Exceptions & KPI

### EP-09 — Monitoring Dashboard & Exception Management

US-09 — User Story

As a Dispatcher/Manager, I want to monitor active trips, delivery statuses, GPS coordinates and exceptions from one dashboard.

| # | Task | Loại | Giờ | Mô tả | Phụ trách |
| --- | --- | --- | --- | --- | --- |
| 1 | Implement GPS update ingestion API | Backend | 10 | Receive lat/lng/timestamp from Driver App/GPS Tracking Platform | BE1 |
| 2 | Implement milestone and e-POD status aggregation | Backend | 10 | Status per stop: pending, arrived, delivered, exception | BE2 |
| 3 | Build monitoring dashboard | Frontend | 14 | Active trips, map/last location, ETA deviation, e-POD status | FE1 |
| 4 | Build exception review screen | Frontend | 8 | Exception list, reason, evidence, dispatcher note | FE2 |
| 5 | Test monitoring and alert cases | Testing | 10 | No GPS, delayed trip, missing e-POD, exception submitted | QA |

Tổng ước lượng US-09: 52 giờ (≈ 8.7 ngày công)

## INC-5 — Trip Monitoring, Exceptions & KPI

### EP-10 — Operational KPI Reporting

US-10 — User Story

As a Logistics Manager, I want KPI reports so I can assess planning efficiency, capacity utilization and delivery reliability.

| # | Task | Loại | Giờ | Mô tả | Phụ trách |
| --- | --- | --- | --- | --- | --- |
| 1 | Design KPI query model | Backend | 8 | Planning time, vehicle utilization, trip count, on-time rate, exceptions | BE1 |
| 2 | Implement KPI APIs | Backend | 10 | Filters by date, route, vehicle, driver | BE2 |
| 3 | Build KPI dashboard | Frontend | 12 | Cards/charts/tables for operational metrics | FE1 |
| 4 | Export KPI report | Frontend/Backend | 6 | CSV/PDF export for management review | FE2/BE1 |
| 5 | Test KPI calculations | Testing | 8 | Known dataset validates utilization and delivery status counts | QA |

Tổng ước lượng US-10: 44 giờ (≈ 7.3 ngày công)

## INC-6 — Driver Mobile App & e-POD

### EP-11 — Driver Trip Execution

US-11 — User Story

As a Driver, I want to view assigned trips, route sequence, product checklist and LIFO unloading instructions on mobile.

| # | Task | Loại | Giờ | Mô tả | Phụ trách |
| --- | --- | --- | --- | --- | --- |
| 1 | Mobile assigned trip list and detail screens | Mobile | 14 | Trip summary, route, active stops, ETA, item checklist | FE2 |
| 2 | Mobile LIFO unloading screen | Mobile | 8 | Stop-by-stop unloading order and item grouping | FE2 |
| 3 | API for mobile trip synchronization | Backend | 10 | Trip payload, cache-friendly response, driver authorization | BE1 |
| 4 | Google Maps/deep link navigation from stop detail | Mobile | 6 | Open navigation to store coordinates | FE2 |
| 5 | Test mobile trip authorization and display | Testing | 8 | Driver sees only assigned trips; cancelled trip hidden | QA |

Tổng ước lượng US-11: 46 giờ (≈ 7.7 ngày công)

## INC-6 — Driver Mobile App & e-POD

### EP-12 — Milestones, Exceptions & e-POD

US-12 — User Story

As a Driver, I want to update milestones, report exceptions and submit e-POD so delivery completion is traceable.

| # | Task | Loại | Giờ | Mô tả | Phụ trách |
| --- | --- | --- | --- | --- | --- |
| 1 | Milestone update API and mobile actions | Backend/Mobile | 14 | Start trip, arrived, delivered, departed stop | BE2/FE2 |
| 2 | e-POD capture mobile flow | Mobile | 14 | Photo capture, receiver signature, timestamp, GPS coordinate | FE2 |
| 3 | e-POD storage and validation service | Backend | 12 | Required proof fields; stop cannot be delivered without valid e-POD | BE1 |
| 4 | Operational exception mobile flow | Mobile/Backend | 12 | Reason code, note, photo evidence, sync to dashboard | FE2/BE2 |
| 5 | Offline draft and retry handling | Mobile | 8 | Local save for no network; sync when online | FE2 |
| 6 | End-to-end UAT test | Testing | 12 | Dispatch → mobile execution → e-POD → monitoring update | QA |

Tổng ước lượng US-12: 72 giờ (≈ 12.0 ngày công)

# 4. Kế hoạch Sprint đã sửa (2 tuần/sprint)

Kế hoạch cũ 7 sprint chỉ phù hợp khi Driver App bị hoãn. Theo Report 1, Mobile App và e-POD nằm trong phạm vi, vì vậy kế hoạch được mở rộng thành 8 sprint để vẫn đảm bảo chất lượng kiểm thử tích hợp.

| Sprint | Tuần | Mục tiêu | Deliverables chính |
| --- | --- | --- | --- |
| Sprint 1 | Tuần 1-2 | Foundation + Auth | BE/FE/Mobile skeleton, DB migration, CI, JWT/RBAC web + mobile login. |
| Sprint 2 | Tuần 3-4 | Master Data | User/Role, Route/Stop, Store GPS, Vehicle m³/kg, Product master. |
| Sprint 3 | Tuần 5-6 | Excel Import | Upload Excel, parse, row validation, import preview, error list. |
| Sprint 4 | Tuần 7-8 | Auto Route Assignment + Trip Draft | Store-to-route mapping, Trip Draft generation, total m³/kg calculation. |
| Sprint 5 | Tuần 9-10 | Trip Review + ETA + Capacity/LIFO | Active/skipped stops, Haversine ETA, dual-constraint validation, LIFO manifest. |
| Sprint 6 | Tuần 11-12 | Dispatch | Vehicle/driver allocation, trip lock, loading/handover slip, dispatch to mobile. |
| Sprint 7 | Tuần 13-14 | Monitoring + KPI | GPS/milestone/e-POD dashboard, exception review, KPI reports. |
| Sprint 8 | Tuần 15-16 | Driver Mobile App + e-POD UAT | Trip detail, LIFO guide, milestones, exception report, e-POD capture, end-to-end UAT. |

# 5. Cân bằng khối lượng theo thành viên

| Nhóm | Trọng tâm công việc | Ghi chú cân bằng tải |
| --- | --- | --- |
| BE1 | DB schema, auth, master data, APIs, e-POD storage | Giữ vai trò backend lead và quản lý migration. |
| BE2 | Excel parser, route assignment, capacity, LIFO, ETA, trip state, exceptions | Khối lượng logic nghiệp vụ cao nhất; cần review kỹ bằng unit test. |
| FE1 | Web dashboard shell, import UI, planning, dispatch, monitoring, KPI | Frontend lead, đảm bảo UX nhất quán. |
| FE2 | Admin screens, master data screens, Driver Mobile App, e-POD flow | Tăng tải so với kế hoạch cũ vì FE-06 không còn Deferred. |
| QA | Test plan, integration tests, UAT scripts, documentation | Tập trung E2E từ import → dispatch → mobile → e-POD → monitoring. |

Tổng ước lượng backlog đã sửa: 678 giờ (≈ 113.0 ngày công). Đây là ước lượng sơ bộ để cập nhật với Project Management Plan sau khi khách hàng xác nhận phạm vi Mobile App.

# 6. Hạng mục Deferred / Out of Scope sau khi sửa

| ID | Hạng mục | Lý do |
| --- | --- | --- |
| LI-01 | Full ERP | Ngoài phạm vi SME-focused delivery management. |
| LI-02 | Accounting & Financial Software | Không xử lý invoice, payroll, tax, general ledger. |
| LI-03 | Fully Dynamic Routing / TSP Optimization | ELog chỉ tối ưu trong fixed-route, không sinh tuyến tự do toàn thành phố. |
| LI-04 | Heavy WMS | Không bao gồm robotic picking, slotting, inventory lifecycle forecasting. |
| LI-05 | Complex 3D Spatial Packing Simulation | Chỉ kiểm tra m³/kg và flat LIFO, không mô phỏng 3D. |
| LI-06 | Manual Order Creation Module | Order input chỉ qua Excel import. |
| LI-07 | Multi-Warehouse & Inter-Warehouse Logistics | Chỉ một kho trung tâm. |

# 7. Rà soát nhất quán & cảnh báo BA/SA

• Cần đổi tên tài liệu từ “Web Dashboard” thành “Web Dashboard & Driver Mobile App” để khớp Report 1.

• Không được để FE-06 trong mục Deferred; FE-06 là feature chính của Iteration 3.

• Các user story về ETA cần ghi rõ dùng Haversine + average speed, không phụ thuộc live traffic API.

• Các story về capacity phải dùng cả volume m³ và weight kg; không chỉ ghi m³.

• Nên cập nhật Project Management Plan nếu timeline chính thức vẫn đang là 7 sprint, vì scope mới có Mobile App và e-POD.

• Cần thống nhất version Report 1 trong tài liệu: file cung cấp tên v1.0.9 nhưng nội dung trang đầu ghi v1.0.8, Last Updated 07/06/2026.

— End of revised plan —